cÖKí mvi ms‡ÿc

1|
cÖK‡íi bvg
t ÒPÆMÖvg †Rjvi DcK~jxq GjvKvi †cvìvi bs-62 (c‡Z½v), †cvìvi bs- 63/1G 


(Av‡bvqviv), †cvìvi bs- 63/1we (Av‡bvqviv Ges cwUqv) cybe©vmb cÖKíÓ |
2|
(K) gš¿Yvjq
t cvwb m¤ú` gš¿Yvjq


(L) ms¯’v
t evsjv‡`k cvwb Dbœqb †evW© (evcvD‡ev)

3|
cÖK‡íi cUf~wg
t


DcK~jxq evua cÖK‡íi AvIZvq PÆMÖvg †Rjvi PÆMÖvg wmwU K‡c©v‡ikb AvIZvf~³ c‡Z½v I nvwjkni, Av‡bvqviv Dc‡Rjv I cwUqv Dc‡Rjvi wekvj GjvKv‡K mvM‡ii D”P †Rvqv‡ii †jvbv cvwb cÖ‡ek‡iva I R‡jv”Qv‡mi aŸsmvZœK ÿqÿwZ n‡Z iÿvKi‡Yi Ges weMZ eQi ¸‡jv‡Z wmWi, AvBjv, bvwM©m, gnv‡mb, †Kv‡gb mn N~wY©So †ivqvby I ‡gviv Ges ZrcieZ©x mvgyw`ªK wb¤œPvcRwbZ DuPz †Rvqv‡ii †XD‡qi AvNv‡Z evua/mx-WvB‡Ki cÖwZiÿv KvR I b`x fv½b †ivaK‡í wewfbœ ¯’v‡b ÿwZMÖ¯’ GjvKv †givgZ I c~bev©mb Ges ewY©Z †cvìv‡ii we`¨gvb GjvKvmg~n wewfbœ cÖvK…wZK `~‡hv©M n‡Z iÿv Kivi Rb¨ evcvD‡ev KZ©„K ewY©Z cÖKíwU cÖYqb Kiv nq|
4|  cÖK‡íi D‡Ïk¨
t


K) cÖvK…wZK `~‡hv©‡M ÿwZMÖ¯’ PÆMÖvg †Rjvi cvwb Dbœqb †ev‡W©i AvIZvaxb †cvìvi bs 62 (c‡Z½v), 63/1G (Av‡bvqviv) Ges 63/1we (Av‡bvqviv I cwUqv) †Z Aew¯’Z AeKvVv‡gv mg~‡ni c~bev©mb|

L) †cvìvi/Dc-cÖK‡íi Kvw•LZ mydj wbwðZKi‡Yi j‡ÿ¨ ÿwZMÖ¯’ AeKvVv‡gv mg~‡ni Kg©ÿgZv cybiƒ×vi KiY|  

5|
cÖKí GjvKv
t 

	wbe©vPbx GjvKv
	wefvM
	‡Rjv
	Dc‡Rjv
	‡cvìvi b¤^i

	288, PÆMÖvg-11
	PÆMÖvg
	PÆMÖvg
	c‡Z½v
	62, 63/1A I 63/1B

	290, PÆMÖvg-13
	PÆMÖvg
	PÆMÖvg
	Av‡bvqviv I cwðg cwUqv
	


06|
cÖK‡íi cÖv°wjZ e¨q t




jÿ UvKvq

	wWwcwc
	Aby‡gv`‡bi ZvwiL
	wRIwe
	cÖKí mvnvh¨
	‡gvU

	g~j
	09-08-2016
	28030.25
	
	28030.25

	2q ms‡kvwaZ
	06-06-2018
	32029.77
	
	32029.77


07|
cÖK‡íi ev¯ÍevqbKvj t


	wWwcwc
	Avi¤¢
	mgvwß

	g~j
	‡g, 2016
	Ryb, 2020

	2q ms‡kvwaZ
	‡g, 2016
	Ryb, 2020


08|
cÖK‡íi cÖavb A½mg~n t




jÿ UvKvq

	µwgK
	cÖavb A½mg~n (wWwcwc Abyhvqx)
	cwigvb
	cÖv°wjZ e¨q

	1|
	evuua/WvBK cybivK…wZKiY/‡givgZ/D”PZv DbœxZKiY 
	 64.329 wKtwgt
	2367.25

	
	b`x Zxi/mx-WvBK msiÿY 
	

9.559
wKtwgt
	23753.32

	2|
	WvBK †¯øvc cÖ‡UKkb 
	

0.700
wKtwgt
	250.00

	3|
	Zxi msiÿY †givgZ KvR 
	

1.393
wKtwgt
	1204.22

	4|
	cvwb wbqš¿Y AeKvVv‡gv †givgZ/cybev©mb 
	

24 wU
	283.06

	5|
	cvwb wbqš¿Y AeKvVv‡gv wbgv©Y 
	

11 wU
	2485.88

	6|
	Lvj cybtLbb 
	14.690 wKtwgt
	171.08

	7|
	G‡cÖvP evua I †K¬vRvi wbg©vY (Lvj 8 wU)
	0.310 wKtwgt
	269.97

	8|
	‡K¬vRvi wbgv©Y 
	

0.120 wKtwgt 
	310.74

	9|
	f~wg AwaMÖnY 
	

5.00
†n±i
	235.50

	10|
	‡WªwRs 
	
2.400 wKtwgt
	499.75

	11|
	e„ÿ †ivcb
	
	50.00

	12|
	Ab¨vb¨
	
-
	149.00

	
	‡gvU
	
	32029.77


09|
cÖK‡íi µgcyÄxf~Z AMÖMwZ t 




jÿ UvKvq

	mgqKvj
	wRIwe
	cÖKí mvnvh¨
	 †gvU Avw_©K
	ev¯Íe (%)

	Ryb, 2018
	11167.76
	
	11167.76
	40.00

	Rvbyqvwi, 2019
	14072.26
	
	14072.26
	47.00

	AMÖMwZ
	2904.50
	
	2904.50
	7.00


10|
eQi Iqvix eivÏ I cÖvwß t

jÿ UvKvq

	A_© eQi
	1g ms‡kvwaZ wWwcwc Abyhvqx
	cÖvß eivÏ

	2016-2017
	245.16
	250.00

	2017-2018
	13480.42
	11000.00

	2018-2019
	12489.79
	6000.00

	2019-2020
	5814.40
	

	‡gvU
	32029.77
	17250.00


[image: image1.png]63/1a - Raipur

Projection : Bangladesh Transverse Mercator

Map of Polder
62, 63/1a, 63/1b & 63/2

Chittagong O & M Circle, BWDB

Legend :

®  District HQ A5/ Railway

°  ThanaHQ /\/ National Highway
A Tl Boundary /\/ OtherRoad
A7 District B /\/ River/Khal
7/ District Boundary

/., ThnaBoundary /N Embankments

@ Polder Name

BANDARBAN District Name

Satkania ThanaName

91 0F VAt WODELUNG

Scale :
i 0 1 2 Kilometers
————

N

asumpura |

Baralia





[image: image2.png]Embankment

River Bank Protection

lope protection
Repair of Bank protection
Existing protective work
Rehabilitation /repair of Sluice A A
Construction of W
Re-excavation of Khal —_—

(Closure & Approach Embankment]
josure & Approach Embankment Existing khal

k re & Approach Embkt.

N

8 N

epair of Bank Image © 2016 TerraMetrics

Protection Work

Image/© 2016 DigitalGlobe
Image © 2016 DigitalGlobe.

‘Google earth




	
[image: image3.emf]
	
[image: image4.emf]a. Polder 62

b. Polder 63/1A

c. Polder 63/1B





































114
27-26 ÒPÆMÖvg †Rjvi DcK~jxq GjvKvi †cvìvi bs-62 (c‡Z½v), †cvìvi bs- 63/1G
113
27-26 ÒPÆMÖvg †Rjvi DcK~jxq GjvKvi †cvìvi bs-62 (c‡Z½v), †cvìvi bs- 63/1G

Project location in Map of Bangladesh











image2.png

i*;;%:k & Bangladesh

Sk

o District Map

§ V/ P S

NAOGAON

i . cazPwR

 NARSINGDI(
'BRAHMANBAI

£ KUSHTIA 7 \ =
WEHERPUR g oraka
i NARAYANGARN 3
b~
. CHUADANGA

. /

S enaoan

MAGURA

" SuaRATRUR cHaNDPUR
mmwun

LAKSMIPUR'
* NOAKHALI

]

&
]
)

Lo

pmupun’ 2 i

SATKHIRA aacerraT || [IHALKAT
 KHULNA o 2

CHITTAGONG

coxs BazaR
alx
Legend ¢

== International Boundary

- District Boundary

Coast Line / River














Project location in Map of Chittagong District









a. Polder 62

b. Polder 63/1A

c. Polder 63/1B







image2.png

I
91°20"

-2 CHITTAGONG
DISTRICT
5 0 10 km
FENI
NOAKHALI
| 220
o
B 0
‘Sandwip
£ 2N
| 220
)

91 ;20’

Mirsharai

)
91°40"

91‘"40'

|
92°00' E

Bay of Bengal

COX'S BAZAR

92“00'

Tripura
(INDIA
KHAGRACHHARI
S 3
SN atikchhari RANGAMATI
:‘:‘
ind - g
X A 8
< | Y
74, r' \Raozan
Hathazart
_t . Rang
i 5 Karnafu®
(N D
ID( l’l:‘ ~ ch
74 :
SEE O
] D\ D Wi
! s - e
o A
| satkar
PATIYA

angy

BANDARBAN

220
20

22¢
00'














