cÖKí mvims‡ÿc

1|
cÖK‡íi bvg
t 
‰fie wifvi †ewmb GjvKvi Rjve×Zv `~ixKiY I †UKmB cvwb e¨e¯’vcbv Dbœqb cÖKí 
2|
(K) gš¿Yvjq
t 
cvwb m¤ú` gš¿Yvjq


(L) ms¯’v
t 
evsjv‡`k cvwb Dbœqb †evW© (evcvD‡ev)
3|
cÖK‡íi cUf~wg
t


‰fie b`xwU gv_vfv½v-cyivZb ˆfi‡ei kvLv b`x| Zv‡nicyi cyivZb ˆfie n‡Z Drcbœ n‡q b`xwU h‡kvi I Lyjbv †Rjv w`‡q cÖevwnZ n‡q †kl ch©šÍ iæcmv b`x‡Z cwZZ n‡q‡Q| `xN© w`b a‡i GB b`xwU AÎ GjvKvi RbM‡bi K…wl , grm¨ Pvl, †hvMv‡hvM I gvjvgvj cwien‡b Ab¨Zg gva¨g wnmv‡e e¨eýZ n‡”Q| PzqvWv½v †Rjvi `vgyiû`v Dc‡Rjv n‡Z h‡kvi †Rjvi †PŠMvQv Dc‡Rjvi Zv‡nicyi ch©šÍ 33.00 wKtwgt `xN© gv_vfv½uv b`xwU fivU n‡q †M‡Q| Gi d‡j ˆfie b`xi Dr‡m cÖevn eÜ n‡q †M‡Q| Gi d‡j b`xwUi †Rvqvi evwnZ cwj R‡g Gi bve¨Zv bó K‡i †d‡j‡Q Ges  b`xwU fivU nIqvi cvkvcvwk cÖ¯’I mswKY© n‡q †M‡Q| evsjv‡`k miKv‡ii gvbbxq cÖavbgš¿x b`xwUi bve¨Zv iÿvi Rb¨ Zuvi wbe©vPbx mfvq cÖwZkÖæwZ cÖ`vb K‡iwQ‡jb| GiB avivevwnKZvq 2013 Bs mv‡j IWM KZ…©K ‰fie b`xi wb®‹vkb e¨e¯’v Dbœq‡bi Rb¨ m¤¢ve¨Zv mgxÿv m¤úbœ nq| m¤¢ve¨Zv mgxÿvi mycvwik Abyhvqx ˆfie b`x cybtLbb I ms‡hvM Lv‡j cybtLbb Gi KvR AšÍ©f~³ K‡i cÖKí cÖ¯Ívebv cÖ¯‘Z Kiv nq|

4|  cÖK‡íi D‡Ïk¨
t


· ‡`‡ki `wÿY-cwðgvÂ‡j †UKmB I mgwš^Z b`x e¨e¯’vcbv|

· ‡mP e¨e¯’vi m¤úªmviY|

· grm¨ Pv‡li Dbœqb|

· wb®‹vkb e¨e¯’vi Dbœqb 

· cÖKí GjvKvi †bŠ-‡hvMv‡hv‡Mi Dbœqb|

5|
cÖKí GjvKv
t 

	wbe©vPbx GjvKv
	wefvM
	‡Rjv
	Dc‡Rjv

	 h‡kvi-3
	Lyjbv
	h‡kvi
	h‡kvi m`i

	 h‡kvi-1
	Lyjbv
	h‡kvi
	‡PŠMvQv

	 h‡kvi-4
	Lyjbv
	h‡kvi
	evNvicvov I AfqbMi|

	PzqvWv½v-1
	Lyjbv
	PzqvWv½v
	m`i

	PzqvWv½v-2
	Lyjbv
	PzqvWv½v
	`vgyiû`v I RxebbMi|


06|
cÖK‡íi cÖv°wjZ e¨q t

jÿ UvKvq
	wWwcwc
	Aby‡gv`‡bi ZvwiL
	wRIwe
	cÖKí mvnvh¨
	‡gvU

	g~j
	16-08-2016
	27281.54
	-
	27281.54


07|
cÖK‡íi ev¯ÍevqbKvj t


	wWwcwc
	Avi¤¢
	mgvwß

	g~j
	RyjvB 2016
	Ryb, 2021


08|
cÖK‡íi cÖavb A½mg~n t

jÿ UvKvq
	µwgK
	cÖavb A½mg~n (wWwcwc Abyhvqx)
	cwigvb
	cÖv°wjZ e¨q

	1|
	Zv‡nicyi n‡Z emyw›`qv ch©šÍ ˆfie b`x cybtLbb  
	92.00 wKtwgt
	19581.09

	2|
	emyw›`qv n‡Z Avd«vNvU ch©šÍ ˆfie b`x †WªwRs
	4.00 wKtwgt
	1392.36

	3|
	eywo ˆfie (Avcvi ˆfie) b`xi m‡u½ gv_vfv½v b`xi ms‡hvM ¯’vc‡bi Rb¨ G¨v®‹v‡fUi Øviv Avcvi ˆfie b`x cybtLbb (Avc ÷x‡g - 16wKtwgt + WvDb ÷x‡g - 17wKtwgt)
	33wKtwgt
	2879.96

	4|
	`vBZjv Lvj c~btLbb
	20 wKtwgt
	2325.58

	5|
	4wU ms‡hvM Lvj cybtLbb
	4.475 wKtwgt|
	176.86

	6|
	h‡kvi kni GjvKvi ˆfie b`xi `yBZx‡i †nwis eÛ iv¯Ív wbg©vb
	10.00 wKtwgt
	272.19

	7|
	Ab¨vb¨
	
	653.50

	
	‡gvU
	
	27281.54 


09|   cÖK‡íi µgcyÄxf~Z AMÖMwZ t

jÿ UvKvq

	mgqKvj
	wRIwe
	cÖKí mvnvh¨
	 †gvU Avw_©K
	ev¯Íe (%)

	Ryb, 2018
	1963.56
	-
	1963.56
	8.00

	Rvbyqvwi, 2019
	2280.14
	-
	2280.14
	10.75

	AMÖMwZ
	316.58
	-
	316.58
	2.75


10|
eQi Iqvix eivÏ I cÖvwß t

jÿ UvKvq
	A_© eQi
	g~j wWwcwc Abyhvqx
	cÖvß eivÏ

	2016-2017
	4412.50
	26.14

	2017-2018
	9777.50
	4500.00

	2018-2019
	8301.36
	10000.00

	2019-2020
	3493.38
	

	2020-2021
	1296.80
	

	‡gvU
	27,281.54
	14,526.14


11|
cÖKí ev¯Íevq‡bi mgm¨v t 

1| h‡kvi kni AÂ‡j A‰ea ¯’vcbv I `L‡ji Kvi‡b b`x Lbb KvR e¨nZ n‡”Q| †Rjv cÖkvmb, h‡kvi Gui m‡½u †hŠ_fv‡e b`xi mxgvbv wba©vib c~e©K A‰ea ¯’vcbvi ZvwjKv cÖbqb c~e©K †Rjv cÖkvm‡Ki `ß‡i †cÖib Kiv n‡q‡Q| D‡”Q‡`i j‡ÿ¨ †Rjv cÖkvm‡Ki `ß‡i †hvMv‡hvM Ae¨vnZ i‡q‡Q|
2| h‡kvi kni AÂ‡j †cŠi †Wª‡bi cvwb, `Lj I ¯øvwm gvwUi Kvi‡b 4_© evi `icÎ Avnevb K‡iI wVKv`vi cvIqv hvqwb|
12| m¤¢ve¨ mgvavb t 

1| Lbb Kv‡R ¯^fvweK AMÖMwZi Rb¨ h‡kvi kni AÂ‡j A‰ea ¯’vcbv D‡”Q` Kiv cÖ‡qvRb|

2| h‡kvi kni AÂ‡ji wKtwgt 54.00 n‡Z wKtwgt 58.00 ch©šÍ As‡ki Rb¨ Avjv`vfv‡e b`x Lbb Ges LbbK…Z gvwU e¨e¯’vi AvB‡Ug a‡i cÖv°jb Aby‡gv`b Kiv cÖ‡qvRb|
[image: image1.jpg]KOTCHANDPUR

wsoN

JHIKARG HA

e

CH Km 46.00, z
KOTWALI (JESSOBERADAR) ¢
Y Z S ¢
%, A N

KALIGAN,

‘;“Qﬁ,ﬁ

)
BAGHER PARA

! talg wal
| L\ ¢ «

‘\ (CH K 20.00 IS

%

%

MV:&:'\&*
53
| NL‘7> 1n

ALIKH
‘\"L,._./-’

VN

”

&/}’e h I CH Km 92. zw
N

PROJECT MAP

Detailed Feasibility Study

for Drainage Improvement

and Sustainable Water

Management of Bhairab
River Basin

Demolishing and
® Reconstruction of
Bridges/Culverts

= Walkway (5km)

Dredging by
- Dredger

Excavation by

Excavator

- Maual Excavation

1 No Excavation
Required

.i Upazila Boundary

0 25 5 10
Km

00vE s 0E

100 80150 200





[image: image2.jpg]400000

425000
1

450000 475000
1

Gangni®

(
o 4
S
"

ﬁmmlm g

i Daulatpure

T NN

ll""’/ﬂ River

7 Chuadang

shandpur @

. \,,/\
P

Study Area Map

Detailed Feasibility Study for
Navigation Improvement and
Sustainable Water Management

of Bhairab River Basin
Legend

International Boundary

650000

District Boundary
1 Project Boundary "
== National Highway w<¢> E
~=—— LGED Road
~——— Other Road ¢

——+ Railways

[ River Network

== Bhairab River

625000

M chal 024 8 1
= Rodgs ™ ™ e [
= Culvert

% Sluice Gate

® Upazilla HQ

istri Q

Madhufhali®

T A i N

@
g
)

Atai River

Figure 2.1 : Map showing the study area














326
71-98 ‰fie wifvi †ewmb GjvKvi Rjve×Zv `~ixKiY I †UKmB cvwb e¨e¯’vcbv Dbœqb cÖKí
323
71-98 ‰fie wifvi †ewmb GjvKvi Rjve×Zv `~ixKiY I †UKmB cvwb e¨e¯’vcbv Dbœqb cÖKí

