cÖKí mvims‡ÿc

1|
cÖK‡íi bvg
t
evsjv‡`‡ki b`x Lb‡bi Rb¨ †WªRvi I Avbylw½K hš¿cvwZ msMÖn cÖKí

2|
(K) gš¿Yvjq
t
cvwb m¤ú` gš¿Yvjq


(L) ms¯’v
t
evsjv‡`k cvwb Dbœqb †evW© (evcvD‡ev)

3|
cÖK‡íi cUf‚wg
t



cÖKíwUi AvIZvq †`‡ki b`b`x mg~‡ni bve¨Zv msiÿ‡bi ¯^v‡_© wb‡¤œv³ As‡k fvM Kiv n‡q‡Q|

· Purchase of Dredger with Discharge Pipe Diameter 650 mm with Accessories – 7 sets.

· Purchase of Dredger with Discharge Diameter 500 mm with Accessories – 4 sets.

· Ancillary Vassals & Equipments – 1 Item.

· Vehicles (Jeep – 2 nos & Double Cabin Pick-up – 3 nos) 

4|
cÖK‡íi D‡Ïk¨
t

The Government has envisaged plan to carry out capital dredging of 18 small and medium rivers in short term (5 years) and medium term (10 years) and all the major river systems including Ganges, Brahmaputra & Meghna in long term (15 years) covering thousands of km; most of the work to be executed to revive and maintain the river systems of the country. In order to sustain the rivers during and after capital dredging operation, maintenance dredging shall have to be done as a routine work. The Present capacity of the BWDB dredger fleet is about 5 million cubic meter annually. But to supplement the planned capital dredging operation and carry out maintenance dredging effectively, the existing capacity of the BWDB fleet shall have to be enhanced to about 30 million cubic meter per year. This DPP envisages procurement of 11 nos. dredgers (with ancillary equipment) to account for about 22.6 million cubic meter dredging capacity annually to meet overall requirement of capital dredging and maintenance dredging in the future.  

5|
cÖKí GjvKv
t
	wbe©vPbx GjvKv
	wefvM
	‡Rjv
	Dc‡Rjv

	-
	-
	-
	-


6|
cÖK‡íi cÖv°wjZ e¨q
t

jÿ UvKvq
	wWwcwc
	Aby‡gv`‡bi ZvwiL
	wRIwe
	cÖKí mvnvh¨
	‡gvU

	130988.10
	21/12/2010
	130988.10
	
	130988.10


7|
cÖK‡íi ev¯ÍevqbKvj
t


	wWwcwc
	Avi¤¢
	mgvwß

	g~j
	RyjvB, 2010
	Ryb, 2012

	1g ms‡kvwaZ
	RyjvB, 2010
	Ryb, 2014

	2q cÖ¯ÍvweZ
	RyjvB, 2010
	Ryb, 2015


8|
cÖK‡íi cÖavb A½mg~n t

jÿ UvKvq
	µwgK
	cÖavb A½mg~n (wWwcwc Abyhvqx)
	cwigvb
	cÖv°wjZ e¨q

	1|
	6814
	Purchase of Dredger with discharge diameter 650 mm with accessories

1. POD-1/LOT-1 (3 sets)

2. POD-1/LOT-2 (2 sets)

3. POD-1/LOT-3 (2 sets)
	7 †mU
	75600.00

	2|
	6814
	Purchase of Dredger with discharge diameter 500 mm with accessories

1. POD-2/LOT-1 (2 sets)

2. POD-2/LOT-2 (2 sets)
	4 ‡mU
	28000.00

	3|
	6807/ 6814/ 6815/ 6823
	Ancillary Vessels and Equipments

1. Purchase of Amphibian excavator

2. Procurement of Tug

3. Etc.
	1 ‡mU

	21580.00

	4|
	
	Ab¨vb¨
	
	5808.10

	
	
	‡gvU
	
	130,988.10


9|
cÖK‡íi µgcyÄxf~Z AMÖMwZ t

jÿ UvKvq

	mgqKvj
	wRIwe
	cÖKí mvnvh¨
	 †gvU Avw_©K
	ev¯Íe (%)

	Ryb, 2015
	35787.04
	-
	35,787.04
	28.55

	‡m‡Þ¤^i, 2015
	35787.04
	-
	35,787.04
	28.55

	A_©eQ‡ii AMÖMwZ
	   0.00
	   0.00
	   0.00
	   0.00


10|
Aby‡gvw`Z wWwcwc Abyhvqx eQi Iqvix eivÏ t

jÿ UvKvq
	A_© eQi
	wWwcwc Abyhvqx
	cÖvß eivÏ  

	2011-2012
	146.00
	146.00

	2012-2013
	7,000.00
	6,650.00

	2013-2014
	10,000.00
	7,500.00

	2014-2015
	113,842.10
	0

	2015-2016
	113,842.10
	23020.00

	‡gvU
	130,988.10
	37,316.00


11|
ev¯Íevqb mgm¨v
t


12|
m¤¢ve¨ mgvavb
t


PAGE  
43
evsjv‡`‡ki b`x Lb‡bi Rb¨ †WªRvi I Avbylw½K hš¿cvwZ msMÖn cÖKí


