cÖKí mvims‡¶c 

1|
cÖK‡íi bvg 
t
cvebv †Rjvi myRvbMi Dc‡Rjvi wewfbœ ¯’v‡b cÙv b`xi evgZxi fv½b‡iva Ges †eov Dc‡Rjvi bMievox nB‡Z KvRxinvU ch©šÍ hgybv b`xi WvbZxi fv½b‡iva

2|
(K) gš¿Yvjq
t 
cvwb m¤ú` gš¿Yvjq


(L) ms¯’v    
t 
evsjv‡`k cvwb Dbœqb †evW© (evcvD‡ev)
3|
cÖK‡íi cUf~wg
t
cÖwZ eQ‡ii eb¨vq cÙv b`xi evgZx‡i cvebv †Rjvi myRvbMi Dc‡Rjvi wm›`yicyi, cw¶i‡gvo, gvScvov, gvwjdv, gvjwdqv, †Mvqvwiqv evRvi, bqvMÖvg, KvgvinvU, †Mvcvjcyi I bvwRiMÄ Ges hgybv b`xi WvbZx‡i cvebv †eov Dc‡Rjvi bMievoxNvU, iNybv_cyi, cÖZvccyi, gyÝxMÄ, Lvbcyiv, `wikixdcyi I KvRxinvU GjvKvi AmsL¨ emZevox, ¯‹zj-K‡jR, iv¯Ív-NvU, gmwR`-gw›`i mn dmjx Rwg b`x M‡f© wejxb nIqvi †cÖwÿ‡Z ewY©Z b`xZxi msiÿY cÖKíwU ïiæ Kiv nq|
4|  cÖK‡íi D‡Ïk¨ t 
· cvebv †Rjvi myRvbMi Dc‡Rjvi wm›`yicyi, cw¶i‡gvo, gvScvov, gvwjdv, gvjwdqv, †Mvqvwiqv evRvi, bqvMÖvg, KvgvinvU, †Mvcvjcyi I bvwRiMÄ GjvKvi cÙv b`xi evgZxi Ges †eov Dc‡Rjvi bMievoxNvU, iNybv_cyi, cÖZvccyi, gyÝxMÄ, Lvbcyiv, `wikixdcyi I  KvRxinvU GjvKvi hgybv b`xi WvbZxi fv½b‡iv‡a b`xZxi ¯’vqxfv‡e cÖwZi¶v K‡i cÙv-hgybv b`xi AeevwnKvi Rbgvby‡li Rvbgvj i¶v KivB cÖK‡íi gyL¨ D‡Ïk¨; 
· cÙv I hgybv b`xi fv½b n‡Z we`¨gvb eb¨v wbqš¿Y euva, KvRxinv‡Ui c~e©-cwðg AvšÍtms‡hvM UªvÝwgkb jvBb, K…wl Rwg I Ab¨vb¨ g~j¨evb m¤úwË i¶v Kiv;
· b`x Zxi msi¶Y Kv‡Ri gva¨‡g cwi‡ekMZ Dbœqb mvab Kiv|
5|
cÖKí GjvKv t 

	wbe©vPbx GjvKv
	wefvM
	‡Rjv
	Dc‡Rjv

	68 cvebv-1
	ivRkvnx
	cvebv
	†eov

	69 cvebv-2
	ivRkvnx
	cvebv
	myRvbMi


6|
cÖK‡íi cÖv°wjZ e¨q t 

jÿ UvKvq
	wWwcwc
	Aby‡gv`‡bi ZvwiL
	wRIwe
	cÖKí mvnvh¨
	‡gvU

	g~j
	26/12/2010
	20089.25
	-
	20089.25

	1g cÖ¯ÍvweZ
	-
	21906.63
	-
	21906.63


7|
cÖK‡íi ev¯ÍevqbKvj t


	wWwcwc
	Avi¤¢
	mgvwß

	g~j
	Rvbyqvix,  2011
	Ryb, 2013

	1g cÖ¯ÍvweZ
	Rvbyqvix,  2011
	Ryb, 2015


8|
cÖK‡íi cÖavb A½mg~n t 

jÿ UvKvq
	µwgK
	cÖavb A½mg~n (wWwcwc Abyhvqx)
	cwigvY
	cÖv°wjZ e¨vq

	1|
	myRvbMi Dc‡Rjvi 11wU ¯’v‡b cÙv b`xi evgZxi  cÖwZi¶vg~jK KvR|
	3.315 wKtwgt
	3927.06

	2|


	‡eov Dc‡Rjvi iNybv_cyi GjvKvq wKwgt 0.00  n‡Z wKwgt 1.520 = 1520wgUvi Ges iNybv_cyi n‡Z KvwRinvU ch©šÍ wKwgt 1.520 n‡Z wKwgt 3.770 Ges wKwgt 5.750 n‡Z wKwgt 9.000= 5500 wgUvi hgybv b`xi WvbZxi cÖwZi¶vg~jK KvR|
	7.020 wKtwgt
	14560.74

	3|
	bMievox n‡Z KvRxinvU ch©šÍ wKwgt 0.000 n‡Z wKwgt 9.000 ch©šÍ hgybv b`xi †WªwRs KvR|
	0.30 wKtwgt
	1344.45

	4|
	Rxc µq (2350 wmwm, 5 `iRv wewkó)|
	1 wU
	51.00

	5|
	mv‡f© I Bb‡f‡÷‡Mkb, ‡c‡Uªvj I jyweª‡K›U, gy`ªb I cÖKvkbv, ‡÷kbvwi Ges hvbevnb †givgZ|
	1 `dv
	36.00

	6|
	Ab¨vb¨ (cÖvBm, wdwRK¨vj Kw›U‡RwÝ I KvR PjvKvjxb iÿbv‡eÿY)|
	1`dv
	170.00

	
	‡gvU
	
	20089.25


9|
cÖK‡íi µgcyÄxf~Z AMÖMwZ t

jÿ UvKvq

	mgqKvj
	wRIwe
	cÖKí mvnvh¨
	 †gvU Avw_©K
	ev¯Íe (%)

	Ryb, 2015
	9699.05
	-
	9,699.05
	50.62

	 †m‡Þ¤^i, 2015
	9699.05
	-
	9,699.05
	50.62

	A_©eQ‡ii AMÖMwZ
	   0.00
	   0.00
	   0.00
	   0.00


10|  eQi Iqvix GwWwc eivÏ I cÖvwß t

jÿ UvKvq
	A_© eQi
	wWwcwc Abyhvqx 
	cÖvß eivÏ

	2010-2011
	3715.34
	200.00

	2011-2012
	8613.31
	2500.00

	2012-2013
	7760.60
	2000.00

	2013-2014
	-
	2200.00

	2014-2015
	-
	2000.00

	2015-2016
	-
	4000.00

	‡gvU
	20,089.25
	12,900.00


11|
ev¯Íevqb mgm¨v t

12|
m¤¢ve¨ mgvavb t


[image: image1.jpg]Location Map of
Padma left bank protection at various location of
Sujanagar and Jamuna right bank protection at
Raghunatpur D/S at old Nagarbari Ghat of
Bera of Pabna District

MYANMAR
21





[image: image2.jpg]Document Path: D:\P0025\Micsellaneous\BWDB_Project\MXD\Pabna.mxd [*mtn*20.04.2014]

fi K\ S handl ariapuf Hat Kaij
3% [ P C\\\.J ~ Faridpur Banwarinaga v SEEE N
NN
r N /
- i Va
. ll j ra_Go Jamirta Hat
l,) [ Ps o
) — ri Hat
. Dhanuaghata Gc / Clelfjor. 2215 SIRAJGANJ
. <
:8 B 'J LJ\ #Lié’,» J\ / ’
< = Bera
Q (8 .
7
( nthia Gc
_) Santhia
.
RN AN | ‘
-~ J | |
U N
R-ataik akalia Gc
|
J\l., |
'7} {
£ _)!r
;Sr B ’\" anagram-G N
PABNA
’1
> —_ Xa ur Ge
Jamuna Right Bank Protection work Nolkhola
. (ch 0.00km to 3.77km & 5.75k to 9.00km) N
: from Raghunathpur to kazirhat area
Sujanagar Ge
TG ‘ ANIKGANJ
Z \'\4\' 1
& 3
Sengram '/\ [ \
USHYIA
yamganj Gc
baspur Hat
|
§ Padma left Bank Protection work at 11 4
‘(EQ 7 different location under sujanagar upazila zirganj Ge
O q
~
[
Pangsa oS
Pangsha Hat 1<
*
BelgachiH tRAJBARl urjanegar Ha
/" & Rajbari
'Arunganj Hat 1,
z ™
2 ~ ~—ar] ] KAtakhali Hat
& agduli Hat /\ Aﬂﬁi\ Yol I e ﬁ\
"
O
RN | j\| & ! | |
89°25'0"E 89°30'0"E 89°35'0"E 89°40'0"E 89°45'0"E
Legend Ministry Of Water Resources Map Area
B DistictHQ || ProjectArea Bangladesh Water Development Board (BWDB)
@ ThanaHQ [____| Upazila Boundary . . .
Padma left bank protection at various location of
©  Growth Center | | Water Body . ) .
—a—a Embankment National Highway Sujanagar and Jamuna right bank protection at Raghunatpur
s Protective work —— Regional Highway D/S at old Nagarbari Ghat of Bera of Pabna District
L___i ZilaBoundary — Other Project Area Map ay of Benga
0 25 5 10 N INSTITUTE OF WATER MODELLING

[ I I, K m
Projection: Bangladeh Transverse Mercator (BTM)

A

















PAGE  
61
cvebv †Rjvi myRvbMi Dc‡Rjvi wewfbœ ¯’v‡b cÙv b`xi evgZxi fv½b‡iva


