cÖKí mvims‡ÿc

1|
cÖK‡íi bvg
t
KzwoMÖvg †Rjvi wPjgvix I Dwjcyi Dc‡Rjvaxb ˆeivMxinvU I wPjgvix e›`i GjvKvq eªþcyÎ b‡`i Wvb Zxi i¶v cÖKí, †dR-2
2|
(K) gš¿Yvjq
t
cvwb m¤ú` gš¿Yvjq


(L) ms¯’v
t
evsjv‡`k cvwb Dbœqb †evW© (evcvD‡ev)|

3|
cÖK‡íi cUf~wg
t

cÖwZ eQ‡ii eb¨vq eªþc~Î b‡`i fqven fv½‡b KzwoMÖvg †Rjvi Dwjcyi I wPjgvix Dc‡Rjvi eû ¸iæZ¡c~b© AeKvVv‡gv b`xM‡f© wejxb nIqv Ges we¯Íxb© GjvKvi dm‡ji cÖPzi ÿwZ nIqvq ewY©Z Zxi msiÿY cÖKíwU ïiæ Kiv nq|

4|  
cÖK‡íi D‡Ïk¨
t

· eªþc~Î b‡`i fqven fv½b n‡Z KzwoMÖvg †Rjvi Dwjcyi Dc‡Rjvi AbšÍcyi I ZrmsjMœ GjvKv Ges wPjgvix Dc‡Rjvi KvP‡Kvj Ges igbvNvU (e¨vsgvivNvU) I ZrmsjMœ GjvKv i¶v Kiv|

· cªKíwU ev¯ÍevwqZ n‡j AvbygvwbK 1510.20 †KvwU UvKvi m¤ú` b`x fv½‡bi SywKgy³ n‡e Ges cªKí GjvKvq mvgvwRK Dbœqb I A_©‰bwZK Kg©KvÛ e„w× cv‡e|

5|
cÖKí GjvKv
t 

	wbe©vPbx GjvKv
	wefvM
	‡Rjv
	Dc‡Rjv

	27 KzwoMÖvg-3
	iscyi
	KzwoMÖvg
	Dwjcyi I wPjgvix


6|
cÖK‡íi cÖv°wjZ e¨q
t 

jÿ UvKvq

	wWwcwc
	Aby‡gv`‡bi ZvwiL
	wRIwe
	wcG
	‡gvU

	g~j
	
	19136.03
	-
	19136.03


7|
cÖK‡íi ev¯ÍevqbKvj
t


	wWwcwc
	Avi¤¢
	mgvwß

	g~j
	b‡f¤^i 2012
	Ryb, 2016


8|
cÖK‡íi cÖavb A½mg~n t

jÿ UvKvq

	µwgK
	wWwcwc Abyhvqx cÖavb A½mg~n
	cwigvb
	cÖv°wjZ e¨q

	1|
	Dwjcyi Dc‡Rjvi nvwZqv BDwbq‡bi AbšÍcyi GjvKvq eªþc~Î  b‡`i Wvb Zxi msiÿY KvR|
	1.50 wKtwgt
	5984.32

	2|
	wPjgvix Dc‡Rjvi ivbxMÄ BDwbq‡bi KvP‡Kvj GjvKvq eªþc~Î b‡`i Wvb Zxi msiÿY KvR|
	1.50 wKtwgt
	5919.82

	3|


	wPjgvix Dc‡Rjvi igbv BDwbq‡bi igbvNvU (e¨vOgvivNvU) GjvKvq eªþc~Î b‡`i Wvb Zxi msiÿY KvR|
	2.00 wKtwgt
	6990.64

	4|
	Ab¨vb¨
	1 `dv
	241.25

	
	‡gvU
	
	19,136.03


9|
cÖK‡íi µgcyÄxf~Z AMÖMwZ t

jÿ UvKvq

	mgqKvj
	wRIwe
	cÖKí mvnvh¨
	 †gvU Avw_©K
	ev¯Íe (%)

	Ryb, 2015
	6843.98
	-
	6,843.98
	42.31

	‡m‡Þ¤^i, 2015
	6843.98
	-
	6,843.98
	44.59

	A_©eQ‡ii AMÖMwZ
	   0.00
	   0.00
	   0.00
	   2.28


10|  eQi Iqvix GwWwc eivÏ I cÖvwß t

jÿ UvKvq
	A_© eQi
	wWwcwc Abyhvqx 
	cÖvß eivÏ

	2012-2013
	300.00
	200.00

	2013-2014
	9120.90
	3000.00

	2014-2015
	-
	3256.00

	2015-2016
	-
	4500.00

	‡gvU
	9,420.90
	10,956.00


11|
ev¯Íevqb mgm¨v
t

12|
m¤¢ve¨ mgvavb
t


[image: image1.jpg]Location Map of
Brahmaputra Right Bank Protection Project at
Bairagirhat and Chilmari Bandar Area
under Chilmari and Ulipur Upazila, Kurigram District
(Phase - 2)" -8

}t{ 2

il

MYANMAR
21





[image: image2.jpg]<3 Study Area

!
i
|
|
i
|
|
i
|
| ~o
! -
! e
. {
! \
! h Tabakpur
L
- ~/"'—\ ~
- - 1 f
' !
| I
1 ‘\ r’|
! [
' L
! i
1 L.
' !
s ' —-————
5 . Lo
g ‘e
-

840'000

Saheber Alg

)’/
s3dhoo

7

Ashtamir Char

T
47&)00

B District Hq

@ Thana Hq
7N\ International Boundary
“"\..- District Boundary
“7\..» Thana Boundary
“\_~ Road
“_ River
“ Railway

P Bank Protection Work

' . Union Boundary

E Water Body

Ministry of Water Resources Fa
Bangladesh Water Development Board (BWDB)

A L

Brahmaputra Right Bank Protection Project at Bairagirhat
and Chilmari Bandar Area Under Chilmari and Ulipur
Upazila, Kurigram District (Phase - 2)

N

INSTITUTE OF WATER MODELLING

08 04 0 038 16
== [(EH

Projection : Bangladesh Transverse Mercator
Path GIS-75\D:\P0020\p40838_PIS_BWDB\ArcGIS\mxd\Kurigram_district_errossion_from_jamuna_Prj_map.mxd [*Lpb* 29.April.14]





PAGE  
117
KzwoMÖvg †Rjvi ˆeivMxinvU I wPjgvix e›`i GjvKvq eªþcyÎ b‡`i Wvb Zxi i¶v cÖKí, †dR-2

