cÖKí mvims‡ÿc

1|
cÖK‡íi bvg
t
cvwb feb wbg©vb (1g ch©vq)

2|
(K) gš¿Yvqj
t
cvwb m¤ú` gš¿bvjq

(L) ms¯’v
t
evsjv‡`k cvwb Dbœqb †evW© (evcvD‡ev)
3|
cÖK‡í cUf~wg
t
1972 mv‡ji gnvgvb¨ ivóªcwZi Av‡`k bs-wcI-59 †gvZv‡eK BwcIqvc`v Gi cvwb Ask wb‡q evsjv‡`k cvwb Dbœqb †evW© (evcvD‡ev) `ywU m¦vqZ¡kvwmZ ms¯’v wn‡m‡e AvZ¥cÖKvk K‡i| evsjv‡`k cvwb Dbœqb †evW© MwVZ nIqvi c~‡e© we`¨yr Dbœqb kvLv Ges cvwb Dbœqb kvLvi mgb¦‡q BwcIqvc`v cÖavb Kvh©vjq gwZwSj¯’ Iqvc`v fe‡b mKj Kvh©µg cwiPvjwZ n‡q Avm‡Q| wKš‘ m¦vaxbZvi cieZx©‡Z cvwb Dbœqb †evW© I we`¨yr Dbœqb †evW© e¨vcKfv‡e cÖmvigvb nIqvq Ges cÖkvmwbK Kvh©µg e„w× cvIqvq gwZwSj¯’ 70,000 eM©dzU AvqZ‡bi Iqvc`v fe‡b ¯’vb msKzjvb bv nIqvq cÖkvmwbK Kvh©µg myôyfv‡e cwiPvjbvi Rb¨ cÖvq 1,20,500 eM©dzU Awdm fvov Ki‡Z nq Ges cÖwZ eQB GBLv‡Z wecyj cwigvb A_© LiP Ki‡Z nq| eZ©gvb Kv‡Ri cwiwa Ges cÖkvmwbK Kvh©µg myôy fv‡e cwiPvjbvi Rb¨ 2,00,000 eM©dzU AvqZb wewkó cvwb Dbœqb †ev‡W©i GKwU wbRm¦ wewìs cvwb feb wbg©v‡bi Rb¨ wWwcwc cÖYqb Kiv nq Ges GK‡bK KZ©„K Aby‡gvw`Z nq| cvwb feb wbg©v‡bi Rb¨ 72 MªxY‡ivW¯’ cvwb Dbœqb †ev‡W©i AwaMªnbK…Z RvqMvq cvwb feb wbg©v‡bi ¯’vb wba©vib Kiv nq| cvwb feb wbwg©Z n‡j cÖkvmwbK Kv‡Ri MwZ e„w× cv‡e Ges fvov eve` cÖwZ ermi miKv‡ii wecyj cwigvb A_© mvkÖq n‡e|

04|
cÖK‡íi D‡Ïk¨
t

cvwb feb wbwg©Z n‡j cvwb m¤ú` mswk­ó c­vwbs, wWRvBb, gwbUwis BZ¨vw` Kvh©µg h_vh_ fv‡e ev¯—evqb Kiv hv‡e Ges cvwb m¤ú` mswk­ó cvwb m¤ú` gš¿bvj‡qi AvIZvfy³ 5wU ms¯’v h_v t evsjv‡`k cvwb Dbœqb †evW©, Iqvi‡cv, ‡RAviwm, nvIi I Rjvfywg Dbœqb †evW©, AviAviAvB (wjqv‡Rv Awdm) Awdm mg~‡ni ¯’vb msKzjvb n‡e| d‡j Awdm fvov eve` miKv‡ii cÖvq 3.50 †KvwU UvKv mvkÖq n‡e|

05|
cÖKí GjvKv
t 

	wbe©vPbx GjvKv
	wefvM
	‡Rjv
	Dc‡Rjv

	185 XvKv-12
	XvKv
	XvKv
	72 Mªxb‡ivW, XvDwmK IqvW©-26, ‡ZRMvuI


06|
cÖK‡íi cÖv°wjZ e¨q t 

jÿ UvKvq

	wWwcwc
	Aby‡gv`‡bi ZvwiL
	wRIwe
	cÖKí mvnvh¨
	‡gvU

	g~j
	02/09/2013
	5637.00 
	-
	5637.00


07|
cÖK‡íi ev¯ÍevqbKvj t


	wWwcwc
	Avi¤¢
	mgvwß

	g~j
	RyjvB, 2013
	Ryb, 2016


08|
cÖK‡íi cÖavb A½mg~n t

jÿ UvKvq

	µwgK
	cÖavb A½mg~n (wWwcwc Abyhvqx)
	cwigvb
	cÖv°wjZ e¨q

	1|
	Awdm feb wbg©vb
	
16265
etwgt
	5625.00

	2|
	Ab¨vb¨
	
1
`dv
	12.00

	
	‡gvU t
	
	5,637.00


09|
cÖK‡íi µgcyÄxf~Z AMÖMwZ t

jÿ UvKvq

	mgqKvj
	wRIwe
	cÖKí mvnvh¨
	 †gvU Avw_©K
	ev¯Íe (%)

	Ryb, 2015
	2000.00
	-
	2,000.00
	37.00

	‡m‡Þ¤^i, 2015
	2000.00
	-
	2,000.00
	45.00

	A_©eQ‡ii AMÖMwZ
	   0.00
	   0.00
	   0.00
	   8.00


10|
Aby‡gvw`Z wWwcwc Abyhvqx eQi Iqvix eivÏ I cÖvwß t

jÿ UvKvq

	A_© eQi
	wWwcwc Abyhvqx
	cÖvß eivÏ

	2013-2014
	400.00
	-

	2014-2015
	2597.10
	1000.00

	2015-2016
	2639.90
	2991.00

	me©‡gvU
	5,637.00
	3,991.00


11|
ev¯Íevqb mgm¨v t

cÖ‡hvR¨ bq|
12|
m¤¢ve¨ mgvavb t

cÖ‡hvR¨ bq|

evsjv‡`‡ki gvbwP‡Î cÖKíwUi Ae¯’vb

[image: image1]
[image: image2.jpg]






























XvKv †Rjv




















PAGE  
120
cvwb feb wbg©vb (1g ch©vq)

[image: image3.png]o
®
o
]

N\ La
Saldpur

Raiganj "\, Dingp

i

National capital
Provincial capital
Town, village

Major airport
International boundary
Provincial boundary
Main road

- Railroad

A

Dingram

e

siaen (|
¥

oo

i . Barisal\ snola N‘"’k
) asma [osbypral AV \jﬁ

Pirbipure, Jha i

\ frayhosy

Dautaghan |

%
- @

orone 4

he
t
of

Matarbari .
Maiskhal |




