cÖKí mvims‡ÿc

01|
cÖK‡íi bvg
t
j¶xcyi ‡Rjvi ivgMwZ I KgjbMi Dc‡Rjv I ZrmsjMœ GjvKv‡K ‡gNbv b`xi Ae¨vnZ fvsMb n‡Z i¶vK‡í b`x Zxi msi¶Y cÖKí (1g ch©vq)
02|
(K) gš¿Yvjq
t
cvwb m¤ú` gš¿Yvjq


(L) ms¯’v
t
evsjv‡`k cvwb Dbœqb †evW© (evcvD‡ev)

03|
cÖK‡íi cUf~wg
t


j¶xcyi ‡Rjvi ivgMwZ I KgjbMi Dc‡Rjv I ZrmsjMœ GjvKv‡K ‡gNbv b`xi Ae¨vnZ fvsMb n‡Z i¶vK‡í Ges D³ GjvKvi ¯’vbxq RbMb I miKvix m¤ú` b`x fvsMb n‡Z iÿv‡_© Av‡jvP¨ cÖKíwU nv‡Z †bqv nq|
04|
cÖK‡íi D‡Ïk¨
t

jÿxcyi †Rjvi ivgMwZ I KgjbMi Dc‡Rjvq evsjv‡`k cvwb Dbœqb †ev‡W©i †cvìvi bs 59/2 iÿvmn b`x fvsMb cÖeb GjvKvq K…wl Rwg, Nievox, evRvi, nvmcvZvj, ¯‹zj-K‡jR Ges miKvix †emiKvix AeKvVv‡gv b`xi Ae¨vnZ fvsMb n‡Z iÿvi gva¨‡g Rbmvavi‡bi gvjvgvj I cÖvK…wZK m¤ú` iÿv I km¨ Drcv`b e„w× cÖK‡íi g~j D‡Ïk¨|
05|
cÖKí GjvKv
t 

	wbe©vPbx GjvKv
	wefvM
	‡Rjv
	Dc‡Rjv

	277-jÿxcyi-4
	PUªMÖvg
	jÿxcyi
	ivgMwZ, KgjbMi


06|
cÖK‡íi cÖv°wjZ e¨q t 

jÿ UvKvq
	wWwcwc
	Aby‡gv`‡bi ZvwiL
	wRIwe
	cÖKí mvnvh¨
	‡gvU

	g~j
	05/08/2014
	19802.042
	-
	19802.042

	1g ms‡kvwaZ
	
	-
	-
	-


07|
cÖK‡íi ev¯ÍevqbKvj t

	wWwcwc
	Avi¤¢
	mgvwß

	g~j
	RyjvB, 2014
	Ryb, 2017

	1g ms‡kvwaZ
	-
	-


08|
cÖK‡íi cÖavb A½mg~n t

jÿ UvKvq

	µwgK
	cÖavb A½mg~n (wWwcwc Abyhvqx)
	cwigvb
	cÖv°wjZ e¨q

	1|
	Zxi msiÿb KvR †givgZ I iÿbv‡eÿb
	
220
wgt
	305.27

	2|
	wgZmywewm Rxc (2300-2500 wmwm)
	
1
wU
	85.00

	3|
	wgZmywewm Wvej †eweb wcK Avc(2300-2500 wmwm)
	
1
wU
	75.00

	4|
	wefvMxq Awdm feb Kvg †ió nvDR wbg©vY
	
1
`dv
	235.00

	5|
	Zxi msiÿb KvR(†jv‡Kkb-1)123.4 n‡Z 112.4 wKtwgt
	
1000
wgt
	2948.34

	6|
	Zxi msiÿb KvR(†jv‡Kkb-2)132.00n‡Z135.50 wKtwgt
	
3500
wgt
	10041.41

	7|
	Zxi msiÿb KvR(†jv‡Kkb-3) 151 n‡Z 152 wKtwgt
	
1000
wgt
	4618.55

	8|
	Pi †WªwRs
	
1000
wgt
	504.00

	9|
	wbg©vY Kvjxb mg‡q cwiPvjb I iÿbv‡eÿb
	
1
`dv
	300.00

	10|
	Ab¨vb¨
	
1
`dv
	689.47

	
	‡gvU
	
	19,802.04


09|
cÖK‡íi µgcyÄxf~Z AMÖMwZ t

jÿ UvKvq
	mgqKvj
	wRIwe
	cÖKí mvnvh¨
	 †gvU Avw_©K
	ev¯Íe (%)

	Ryb, 2015
	5894.35
	-
	5,894.35
	29.77

	‡m‡Þ¤^i, 2015
	5894.35
	-
	5,894.35
	29.77

	A_©eQ‡ii AMÖMwZ
	   0.00
	   0.00
	   0.00
	   0.00


10|
Aby‡gvw`Z wWwcwc Abyhvqx eQi Iqvix eivÏ I cÖvwß t

jÿ UvKvq
	A_© eQi
	wWwcwc Abyhvqx
	cÖvß eivÏ

	2014-15
	10292.81
	6000.00

	2015-16
	6133.13
	12800.00

	2016-17
	3376.10
	-

	me©‡gvU
	19,802.04
	18,800.00


11|
ev¯Íevqb mgm¨v t
Av‡jvP¨ cÖKíwU ev¯Íevq‡bi j‡ÿ¨ evsjv‡`k †mbv evwnbx‡K wb‡qvM c~e©K gš¿bvj‡qi wm×všÍ †gvZv‡eK wWwcwc‡Z OTM c×wZi cwie‡Z© DPM c×wZ‡Z 2014-15 A_© eQi n‡Z KvR ev¯Íevqb ïiæ Kiv n‡q‡Q Ges GZ`wel‡q MZ 19/04/2015 Zvwi‡L evsjv‡`k ‡mbvevwnbxi ms‡M evsjv‡`k cvwb Dbœqb †ev‡©Wi g‡a¨ GKwU Pzw³ bvgv m¤úvw`Z n‡q‡Q| (i) cÖK‡íi KvR PjvKvjxb mgq gvP©/2015 gv‡m †k‡li w`‡K †mbv evwnbx KZ…©K †¯øv‡c eøK †cøwms Gi KvR ïiæ Kivi D‡`¨vM †bq| wKš‘ ‰eix AvenvIqvi Kvi‡b b`x‡Z Ó0Ó(ïb¨) †j‡fj n‡Z cÖvq 2wgUvi D”PZvq cvwb e„w× cvq| b`x‡Z D”P †Rvqvi Ges cÖPÛ †UD‡qi Kvi‡b gvwU fivU I wdëvi g¨v‡Uwiqvjmn eøK ¯’vcb Kiv m¤¢e nqwb| ZvB wWRvBb ms‡kva‡bi cÖ‡qvRbxqZv †`Lv †`q| (ii) Zx‡ii we`¨gvb MÖvDÛ c‡q›U †_‡K bKkvq wb‡`©wkZ `icÎ Zdwmjf‚³ Wvw¤ús ¯’vb ch©šÍ RvqMv UzKz D”P †Rvqvi I †UD‡qi AvNv‡Z fv½‡bi cÖebZv cwijwÿZ nq| weMZ A_© eQ‡ii b¨vq GeviI KvswÿZ jÿgvÎv Abyhvqx cÖK‡íi KvR ev¯Ívevqb Kiv m¤¢e g‡g© Avkv Kiv hvq| eZ©gv‡b cÖK‡íi KvR Pjgvb i‡q‡Q Ges AvcvZZt †Kv‡bv mgm¨vw` cwijwÿZ n‡”Q bv|  

12|
m¤¢ve¨ mgvavb t

(i)
`yB ‡jqvi 50 †KwR gvwU fwZ© M¨vwb e¨vM Gi Dci GK †jqvi 175 ‡KwR evwj fwZ© wRI e¨vM †Uv †_‡K 2wgUvi ch©šÍ ¯’vc‡bi gva¨‡g evu‡ai †Uv †K stabilized Kiv ‡h‡Z cv‡i|
(ii)
D”P †Rvqvi I †UD‡qi AvNv‡Z evu‡ai Xvjmn Zx‡ii fv½b iÿvK‡í 250 wKwR I 175 †KwR wRI e¨vM ¯’vcb Ges 10x2 wgUvi mvB‡Ri wRI wUDe cÖwZ¯’vc‡bi gva¨‡g fv½b cÖebZv cÖwZnZ Kiv ‡h‡Z cv‡i|
gvbwP‡Î cÖK‡íi Ae¯’vb
[image: image1.jpg]'.A
x;.,oa.

S ;
}. A
* —ﬂ ‘ o‘ \.AQ\J‘ ‘ﬂﬂn M’
¥ .A..: ...:: A .-».:

\a .a\ _fp: na.x\o*an A

A.; ¢
- ..‘m‘.: f.. A .AA-:...
: -..,f\»!P\ pr.-\,\o‘.\- i% ~
4 .o » m4 .m ,‘.n
VI, LA “ f: AT TRA” .A
Wi |
N.A,\O.Anmm*ﬂf\. —A\o n\» A-
-.A .Ao‘: ¢-A..— ‘A:.ﬂn 9
a4 .,:.Al. .:.,_...
$Y’ L \a A
. 3 .A..... X .q
~, :..:c. ﬁ..,x..”.
i f..
L 7% a
u.;mm_ « 3 .«;. ..A:ﬂ

Ramgati Nuria Hajir Hat

3.4 . ha_ -A‘: . a A
"mwﬂ.".. P 3 :.‘.w,...?nm, _.:M_..“.
4 e n‘.nnn..-n n W q.
hﬁ NUAﬁ.-n. “. “ﬂkgoﬂﬂ.n MA ‘-.-“_AA; 0‘ a 4:
& k\ oaﬂ...omuwn....z.um .. { »J.xsn .A! ¢ A ean
34 nx A.«{.n..

t Phase-2

Kamal Nagar

Revetment Phase-3
ry

1
:
L
Q.
€
@
E
®
>
)
1

— P.59-2 Bounda

Map showing

Proposed Revetment Location at Three (3) Phases
East Kadir Por{diter Hat
Bankline_2012
Road Network
River Network

a HQ
Proposed_
Proposed_Revetmen

Chainage Location

® Upazil

Bottli Bazar Munshir Hat k Torabganj Bazar

West Kadir Ponditer HatChar
—— Proposed

Kamal Nagar
aneber Bazar

© b e
% ot U8
: ol :
m 2 g
6, “
¥
£
f: Vol IR, AP ®
T o I : g E g 8 .3 %
4557 S & x L : £ £ £ E o =
A o m A fo PR e ' > 48 - - % % 9 N 2 N N v 9
1 }-u.&: N * ..:¢A.:.4: .q.. m s P i G, S oo rbow DT a™
v.A.«.}&a.....{.\v ‘4 ,\.a..afa-..u: . = - M 5 = £ e m £ < @ - & 0
a.dqw : .Afa: onm *nuu 4 ; ﬂnﬂﬁ\a.aﬁ: 4Aa¢.p.. \n Au .M 4 b b » »
g m..uw § p: M\... .mt' ~ :.. (> A~.o. ¢ .-..n\- .q\u *s p! 4 - - ~ ~ ot W ..M
rm 1.,. ..ﬂ.: .:.. .fm .%.. ¥ V\ C m. f: a. C...q.. - s 5 5 s & =]
2 4} A» .\.:f? .m\ AN .‘ F4% £~pr. F ] .m - - - - — -
M 5 ‘ ' LA L mn % o - " ® = = = ]
.-.(: ,: z.: AR .\f: ....q{ ‘(e .qn}...-{.... : f: .‘f: Wl g 8 3 8 8 8 3
ux..f,: i }_M At 7 it .1.,. fee uied Qoled .1} Pl S - o - = - ~
- ‘ {
..,_.A.: tafay 1, A ,.A.:m -:: .: }: .{.. ...e..:m.‘.p b3 - ™
) O m\..ua:!upm»o.unx:.«n«’.o ﬁn\ .o;m\!wn:. .m Q ~ m
N VT .‘(&...:..:M.‘ .n.q.ﬁ« AL ..q g i m .
.A.M“A% ..p. .am\ \f.«n ’» .MA-oaA .mvf —AM’ ..A‘ﬂ“-ﬁ..“v m a .m a.
YOd AR Y U YA L VR A Y R Ay
1% 4 nﬂo‘.. a ‘q»‘ .\..fa.—.\‘\!“ npd...-

. 00002Zs 000008




PAGE  
145
j¶xcyi ‡Rjvi ivgMwZ I KgjbMi Dc‡Rjv I ZrmsjMœ GjvKv‡K ‡gNbv b`xi Ae¨vnZ fvsMb n‡Z i¶vK‡í b`x Zxi msi¶Y cÖKí (1g ch©vq)  

