Office of the Executive Engineer

Tangail O & M Division

BWDB, Tangail
Addendum to the Tender Document for Tender

No: 06/2010-2011 for Dredging of River Jamuna from upstream 
of Bangabandhu Bridge to Daleswari Offtake, Upazila: Bhuapur and Kalihati, Dist: Tangail

Addendum No.01
Following corrections/amendments are made in the Tender Document  of  the  Tender No: 06/2010-2011 for Dredging of River Jamuna from upstream of Bangabandhu Bridge to Daleswari Offtake, Upazila: Bhuapur and Kalihati, Dist: Tangail invited by Executive Engineer, Tangail O&M Division,BWDB, Tangail vide his memo no. T-6/2408 date 09-06-2011: 

i) The Defect Liability Period as specified in GCC 57.1 is amended as follows:

	Clause No

Page No.
	The Defect Liability Period as per Original Document
	The Defect Liability Period as per amendments



	GCC 60.2

70
	1  For the dredged Channel-  6 months

2  For the disposed earth/

    reclaimed area-                   12 months
	1.  For Dredged Channel : 0 (zero) month

2.   For disposed earth     : 06 (six) months


ii    The 2nd Para under Clause 1.32 (Disposal of Dredged Materials ) of Particular Specification, Section-8 , Page No.120  which is read as 

“The spoil disposed must be leveled, compacted to its maximum dry density and properly dressed. In this operation the contractor must deploy necessary earth moving and compacting equipment like crawler tractor, vibratory compactor etc. as deemed fit as per direction of Project Director”

is replaced by
 “The spoil disposed must be leveled, compacted to its natural density and properly dressed. In this operation the contractor must deploy appropriate earth moving and compacting equipment like crawler tractor, vibratory compactor etc.    

iii
Para (1) under Clause 1.03 (Dredging Method) of Particular Specification, Section-8 , Page No. 114 which is read as :
“The Operational mode aims at making optimum use of the available excavation capacity in combination with the erosive forces of water flow, the latter especially in the earlier stage of the recession period. For this purpose dredging is predominantly be done in downstream direction. The manner in which the dredging is executed shall be in accordance with Contractor’s approved method statement”

is amended  as follows 

“The Operational mode aims at making optimum use of the available excavation capacity in combination with the erosive forces of water flow, the latter especially in the earlier stage of the recession period. For this purpose dredging is preferably be done in downstream direction if the situation permit. The manner in which the dredging is executed shall be in accordance with Contractor’s approved method statement”

iv
ITT 17.1 , Page No.31 is amended as follows:
ITT Sub-Clause 17.1(a) in the 1st Column and 1st row under heading “Name of the Equipment” in Page No.31 which is read as

‘Cutter Suction Dredger (must be owned)”

is amended as follows”   

“Cutter Suction Dredger (must be owned).The Dredgers owned by the Tenderer must be free from all defects and in good running condition. Those should be readily deployable in dredging work under the Contract as soon as work order is issued.” 
All other terms and conditions and contents of the Tender Document will remain unchanged. 

This Addendum is issued in pursuant to ITT Sub-Clause No.11.1 and shall form an integral part of the Tender Document as per ITT Sub-Clause No.11.2




     (I.M.REAZUL HASAN )

Executive Engineer

Tangail O&M Division 

BWDB, Tangail

Memo No.T-6/26(40)

Dated 07-07-2011
Copy for favour of kind information/ information and wide circulation to :

01 The Director General, C.P.T.U , Planning Commission, Block-12 (2nd floor) , Sher-E-Bangla Nagar, Dhaka.

02 The Additional Director General, East  Region, BWDB, Dhaka
03 The Additional Director General, West Region, BWDB, Dhaka
04 The Chief Engineer, Central Zone, BWDB, Dhaka 
05 The Project Director, Project Management Unit, Capital (Pilot) Dredging of the River system in Bangladesh, 72, Green Road, BWDB, Dhaka. 

06 The Metropolitan Police Commissioner of Dhaka (DMP). He is requested to please provide all kind of security on 26-07-11 at the Office of the Project Director, Project Management Unit, Capital (Pilot) Dredging of the River system in Bangladesh, 72, Green Road,  BWDB, Dhaka in c/w the tender process.

07 The Director, Contract & Procurement Cell, BWDB, WAPDA BHABAN,( 9th Floor), Motijheel, C/A, Dhaka

08 The Superintending Engineer, Mymensingh O&M Circle, BWDB, Mymensingh .

09 The Deputy Commissioner Tangail

10-12 The Executive Engineer,  O&M Division, BWDB, Mymensingh/Jamalpur/ Netrakona. 

13 The Executive Engineer, WD Division, BWDB, Kishoregonj/Tangail.
14-16 The Executive Engineer, LGED/PWD/R&H, Tangail

17 System Analyst, Computer Section, Chief Monitoring Office, BWDB, WAPDA BHABAN,( 3rd Floor), Motijheel, C/A, Dhaka. He is requested to arrange all necessary action to publish the Addendum  in website of C.P.T.U (CD enclosed)

18 The Accounts Officer, Regional Accounting Centre (RAC), BWDB, Mymensingh

19-20 The Sub-Divisional Engineer, Tangail O & M Sub-Division-1/2 BWDB, Tangail

21-22 The Upazila Nirbahi Officer, Bhuapur/Kalihati in the District of Tangail

23 The Manager, Janata Bank Ltd. 29 Dilkusha Corporate Branch, Dilkusha C/A Dhaka-1000 along with 10(ten) sets of  Addendum No.01 for  each Lot, (Total 30 Nos.)  are sent herewith for attaching with the unsold Tender Document
24-25 Estimator/Asstt. Accountant/ Head Clerk. Of this Division

26
Notice Board

27
Mr./Mrs……………………………………



(I.M.REAZUL HASAN)

Executive Engineer

Tangail O&M Division

BWDB, Tangail
